# Project Planning Phase

# Project Planning

| Date | 25 June 2026 |
| --- | --- |
| Team ID |  |
| Project Name | Smart Agricultural Production Optimization Engine (OptiCrop) |
| Maximum Marks | 5 Marks |

## Product Backlog, Sprint Planning & Estimation

The Smart Agricultural Production Optimization Engine (OptiCrop) project is planned using the Agile Scrum methodology. The complete project is divided into four development sprints. Each sprint contains one or more epics that are further divided into user stories. Story points are estimated using the Fibonacci sequence (1, 2, 3, and 5) to represent the relative effort required to complete each task.

### Product Backlog:

| Sprint | Functional Requirement (Epic) | User Story No. | User Story / Task | Story Points | Priority | Team Member(s) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Dataset Preparation | USN-1 | Collect and organize the crop recommendation dataset. | 2 | High | Sri Teja |
| Sprint-1 |  | USN-2 | Load the dataset into the machine learning environment. | 1 | High | Sri Teja |
| Sprint-1 | Data Preprocessing | USN-3 | Handle missing and inconsistent values. | 3 | High | Sri Teja |
| Sprint-1 |  | USN-4 | Perform feature preprocessing and prepare training data. | 3 | High | Sri Teja |
| Sprint-1 |  | USN-5 | Split the dataset into training and testing sets. | 2 | High | Sri Teja Manikanta |
| Sprint-2 | Machine Learning Model | USN-6 | Train Decision Tree model. | 2 | Medium | Manikanta |
| Sprint-2 |  | USN-7 | Train K-Nearest Neighbour model. | 2 | Medium | Manikanta |
| Sprint-2 |  | USN-8 | Train Logistic Regression model. | 2 | Medium | Manikanta |
| Sprint-2 |  | USN-9 | Train Random Forest model. | 3 | High | Manikanta |
| Sprint-2 | Model Evaluation | USN-10 | Compare model performance and select the best model. | 3 | High | Manikanta |
| Sprint-2 |  | USN-11 | Save the trained model as model.pkl. | 1 | High | Manikanta |
| Sprint-3 | Flask Backend | USN-12 | Develop the Flask application structure. | 3 | High | Manikanta Sri Teja |
| Sprint-3 |  | USN-13 | Implement the prediction module using the trained model. | 3 | High | Manikanta |
| Sprint-3 |  | USN-14 | Validate user input and handle prediction requests. | 2 | High | Manikanta Sri Teja |
| Sprint-3 | Frontend Development | USN-15 | Design the HTML/CSS user interface. | 3 | High | Sri Teja |
| Sprint-3 |  | USN-16 | Display crop recommendation results. | 2 | Medium | Sri Teja |
| Sprint-4 | System Integration | USN-17 | Integrate frontend, backend, and machine learning model. | 5 | High | Manikanta Sri Teja |
| Sprint-4 |  | USN-18 | Perform system testing and validation. | 3 | High | Manikanta Sri Teja |
| Sprint-4 |  | USN-19 | Resolve defects and improve application stability. | 2 | Medium | Manikanta Sri Teja |
| Sprint-4 | Deployment | USN-20 | Prepare the final application for demonstration and deployment. | 2 | High | Manikanta Sri Teja |

## Sprint Tracker :

| Sprint | Planned Story Points | Duration | Sprint Start Date | Planned End Date | Story Points Completed | Actual Release Date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 11 | 1 Day | 26/06/26 | 26/06/26 | 11 | 26/06/26 |
| Sprint-2 | 13 | 2 Days | 26/06/26 | 28/06/26 | 13 | 28/06/26 |
| Sprint-3 | 13 | 2 Days | 29/06/26 | 30/06/26 | 13 | 01/07/26 |
| Sprint-4 | 12 | 1 Day | 01/07/26 | 01/07/26 | 12 | 02/07/26 |

## Velocity:

Planned Total Story Points = 49

Number of Planned Sprints = 4

Planned Velocity = 49 ÷ 4 ≈ 12 Story Points per Sprint

- Actual Velocity after Sprint-1: 11 Story Points

- Actual Velocity after Sprint-2: 13 Story Points

- Actual Velocity after Sprint-3: 13 Story Points

- Actual Velocity after Sprint-4: 12 Story Points

- Average Actual Team Velocity: 12.25 Story Points per Sprint

## Burndown Chart

Burndown Chart Data:

| Timeline Milestone | Date (Actual) | Planned Remaining Points | Actual Remaining Points | Status / Notes |
| --- | --- | --- | --- | --- |
| Project Start | 26/06/26 | 49 | 49 | Project kickoff |
| After Sprint-1 | 26/06/26 | 38 | 38 | Completed 11 SP (Dataset & Preprocessing) |
| After Sprint-2 | 28/06/26 | 25 | 25 | Completed 13 SP (ML Modeling) |
| After Sprint-3 | 01/07/26 | 12 | 12 | Completed 13 SP (Backend & Frontend) — 1 day delay |
| After Sprint-4 | 02/07/26 | 0 | 0 | Completed 12 SP (Integration & Deployment) — 1 day delay |

Burndown Visualization: